# LoS Regression – Change Impact Analysis

## Business problem:

NCL has observed a consistent increase in long Length of Stay (LoS) over the past 5 years (Average LoS +23% between Apr-19 and Apr-24). Increasing length of stay means a higher capacity is needed for the same demand which causes system strain.

Stakeholders are interested in understanding why length of stay has increased within NCL so that that can introduce appropriate measures to reduce it.

## Solution proposed

This project proposes to develop a causal model that can be used to identify relations between admission features, operations and length of stay. The model will be used to understand site level drivers to estimate the potential impact of proposed interventions.

Potential questions/estimands:

- How has LoS changed over the last 4 years in NCL? How does that compare to other ICBs?

- What are the proposed drivers of these changes?

- In the last 2 years, how much of that change has been driven by changes in:

  - Patient health?

  - Operational factors?...

## Key Aims:

- Build a qualitative model of the drivers of Length of Stay in acute providers in NCL

- Data audit,

- Collation/wrangling (build exploratory dataset)

- Exploratory data analysis (describe changes in LoS)

- Read literature regarding known drivers of LoS and methods used to investigate similar problems (I’ve looked super fast so these are mostly about predicting not understanding, but to give you a sense of the kind of literature)

  - Example of paper for predicting LS A systematic review of the prediction of hospital length of stay: Towards a unified framework | PLOS Digital Health

  - Variables affecting hospital length of stay: a scoping review | Emerald Insight

  - Time-to-event modeling for hospital length of stay prediction for COVID-19 patients - ScienceDirect (this is just a fun type of modelling)

  - Causal determinants of postoperative length of stay in cardiac surgery using causal graphical learning - ScienceDirect

- Draw DAG (understand what influences LoS)

- Clearly define estimand(s)

- Decide boundaries of the model

- Speak to stakeholders to confirm model structure and levers available

- Build a quantitative model(s) of LoS

- Build a synthetic dataset for testing

- Explore bayesian hierarchical model to estimate LoS at each site? / structural causal modelling (adjustment for time series?) / other?

- Build model and test on synthetic data. Validate and refine.

- Interpret model/effects etc to draw conclusions

- Produce an output report that summarises findings

- Use this insight to identify where the growth in LoS originated from and opportunities to reduce LoS trends.

- Model changes in LoS in response to interventions (stretching)

- Add functionality to simulate changes in admission demographics to reflect proposed service changes (i.e. if a project aiming to reduce elderly admissions by 10%, what impact of the LoS trends will this have?).

- Validate

- Develop an interactive web app to allow users to interact with model and change interventions

- Put assumptions on length of stay into simple system dynamic model to help understand impact of interventions on bed capacity (Out of scope?)